## 專案管理方式
項目 | 內容 | 執行方式 | 頻率 | 日期 | 時間 | 是否完成 | 負責單位 | 參與人員 | 備註
專案進度報告 | 依據專案時程表追蹤項目狀態，寄送專案工作時程表追蹤當前進行項目內容 | 電子信件 | 每週 |  | 週五，16:00 |  | Metaage | LineBank/ACS/ /Oracle/Metaage
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
週五，16:00
專案進度會議 | 依據專案時程表更新整體專案進度，解決專案執行問題 | LineBank現場會議 | 每週 | 2026-06-04 | 週四，14:00 | Done
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00
週四，14:00

## 專案WBS
紅字 | 待細項
藍字 | 調整內容
*Oracle ACS 啟動日：2026/7/20
項次 | 工作項目 | 天數 | 環境 | 預計完成日 |  | 實際完成日 |  | 專案進度 (Ststus) | 負責單位 | 協辦單位 | 備註
|  |  |  | 開始 | 結束 | 開始 | 結束
0-1 | 前置準備與專案啟動 |  |  | 2026-05-01 | 2026-07-10
0-1-1 | 合約簽署&下單 | N/A | N/A | 2026-05-01 | 2026-05-31 | 2026-05-11 | 2026-05-29 | Done | MetaAge | LineBank
0-1-2 | OEDA完成 | 7 | PROD | 2026-06-15 | 2026-06-23 |  |  |  | LineBank | Oracle/MetaAge
0-1-3 | Site Check for Exadata X11M-Z | 1 | PROD | 2026-06-17 | 2026-06-17 |  |  |  | Oracle System | MetaAge/LineBank | 約佈線廠商一同
0-1-4 | Infra/IT外圍應用系統盤點及防火牆所需申請 | 10 | PROD | 2026-06-24 | 2026-07-07 |  |  |  | LineBank | Oracle/MetaAge
0-1-5 | 主機房空間確認 | 1 | PROD | 2026-06-24 | 2026-07-07 |  |  |  | LineBank | Oracle/MetaAge | *1週內/Exadata到貨前完成
0-1-6 | 機房電力需求與佈線確認 | 1 | PROD | 2026-06-24 | 2026-07-07 |  |  |  | LineBank | Oracle/MetaAge | *1週內/Exadata到貨前完成
0-1-7 | 機房網路架構設定確認 | 2 | PROD | 2026-06-24 | 2026-07-07 |  |  |  | LineBank | Oracle/MetaAge | *1週內/Exadata到貨前完成
0-2 | 專案啟動階段 |  |  | 2026-05-28 | 2026-06-25
0-2-1 | 專案起始日 | 1 | N/A | 2026-05-28 | 2026-05-28 |  |  |  | MetaAge | N/A
0-2-2 | 召開專案啟動會議 | 1 | N/A | 2026-06-17 | 2026-06-17 |  |  |  | MetaAge/LineBank | Oracle | 6/15 15:00-16:00 or 6/17 14:00-15:00(6/17優先)
0-3 | 硬體建置階段 |  |  | 2026-07-15 | 2026-07-28 | [5 empty] | *海運抵達日(OPS預計)：2026/7/13
0-3-1 | Exadata 運送到位 | 1 | PROD | 2026-07-15 | 2026-07-15 |  |  |  | Oracle System | MetaAge/LineBank
0-3-2 | Exadata 定位與cooling | 2 | PROD | 2026-07-16 | 2026-07-17 |  |  |  | Oracle System | MetaAge/LineBank
0-3-3 | Exadata 安裝建置 | 7 | PROD | 2026-07-20 | 2026-07-28 |  |  |  | Oracle System | MetaAge/LineBank | *Oracle 安裝報告
0-3-4 | 安裝Imperva、防毒與NBU | 5 | PROD | 2026-08-03 | 2026-08-07 |  |  |  | LineBank | Oracle System
0-3-5 | 安裝新版EMCC環境 | 5 | PROD | 2026-08-03 | 2026-08-07 |  |  |  | MetaAge | LineBank
第一階段 - EDW(IFRS)作業
1-1 | UAT移轉階段 |  |  | 2026-07-01 | 2026-09-30 | [5 empty] | *8月底完成
1-1-1 | Site Check for Oracle ODA X8-HA | 3 | UAT | 2026-07-01 | 2026-07-03 |  |  |  | MetaAge | LineBank
1-1-2 | Oracle ODA X8-HA 升級 | 3 | UAT | 2026-07-04 | 2026-07-08 |  |  |  | MetaAge | LineBank | *升級版本建議19.31
1-1-2-1 | ELN UAT備份 | 0 | UAT | 115/7/4 | 115/7/5 |  |  |  | LineBank
1-1-2-2 | ODA X8-HA 升級 | 4 | UAT | 2026-07-06 | 2026-07-09 |  |  |  | MetaAge | LineBank | SCAN Name 重新設定, 與升級同步完成
1-1-2-3 | ELN UAT 打補丁 | 1 | UAT | 2026-07-10 | 2026-07-10 |  |  |  | MetaAge | LineBank
1-1-3 | Imperva、防毒與NBU等版本相容性確認 | 5 | UAT | 2026-07-13 | 2026-07-17 |  |  |  | LineBank
1-1-4 | Infra/IT外圍應用系統盤點及防火牆所需申請 | 5 | UAT | 2026-07-20 | 2026-07-24 |  |  |  | LineBank
1-1-5 | ELN資料庫：ODA UAT驗證與升級 | 21 | UAT | 2026-08-03 | 2026-08-31 |  |  |  | Oracle ACS | MetaAge | *ELN升級移轉程序
1-1-5-1 | ELN資料庫：AP測試 | 21 | UAT | 2026-08-03 | 2026-08-31 |  |  |  | LineBank | Oracle ACS | *1個月內完成測試
1-1-6 | EDW(IFRS)資料庫：移轉ODA UAT驗證與升級 | 37 | UAT | 115/7/23 | 115/9/11 |  |  |  | Oracle ACS | MetaAge | *EDW升級移轉程序
1-1-6-1 | 資料面Precheck | 10 | UAT | 115/7/23 | 115/8/7 |  |  |  | LineBank | Oracle ACS
1-1-6-2 | 19c資料庫新增與OGG安裝 | 2 | UAT | 2026-07-23 | 2026-07-24 |  |  |  | Oracle ACS | Oracle ACS / MetaAge
1-1-6-3 | EDW(IFRS)資料庫升級OGG資料同步作業 | 5 | UAT | 115/7/27 | 115/7/31 |  |  |  | Oracle ACS | LineBank
1-1-6-4 | EDW(IFRS)資料庫升級資料面檢查 | 2 | UAT | 115/8/3 | 115/8/4 |  |  |  | Oracle ACS | LineBank | 比對資料庫物件數量、Table筆數以及資料內容抽樣
1-1-6-5 | CBK資料同步OGG資料同步作業 | 3 | UAT | 115/8/5 | 115/8/6 |  |  |  | Oracle ACS | LineBank | 比對Table筆數以及資料內容抽樣
1-1-6-6 | CBK資料同步資料面檢查 | 1 | UAT | 115/8/7 | 115/8/7 |  |  |  | Oracle ACS | LineBank
1-1-6-7 | EDW(IFRS)資料庫：AP測試 | 20 | UAT | 2026-08-10 | 2026-09-04 |  |  |  | LineBank | Oracle ACS | *1個月內完成測試
1-1-6-8 | ODA UAT 加入 EMCC 監控 | 5 | UAT | 2026-08-10 | 2026-08-14 |  |  |  | MetaAge | LineBank
1-1-6-9 | EDW(IFRS)升級移轉 RunBook產出 | 2 | UAT | 2026-09-07 | 115/9/11 |  |  |  | LineBank | Oracle ACS / MetaAge
1-1-6-10 | 關閉舊版EDW資料庫連線 | 0 | UAT | 115/9/11 | 115/9/11 |  |  |  | LineBank | MetaAge
1-1-6-11 | UAT升級移轉過程檢討與經驗整理 | 6 | UAT | 2026-09-07 | 115/9/11 |  |  |  | LineBank | Oracle ACS / MetaAge
1-2 | CBK測試階段 |  |  | 2026-08-03 | 2026-09-11
1-2-1 | CBK資料庫在Exadata環境的功能測試(效能、快照測試) | 8 | POC | 2026-08-03 | 2026-09-11 |  |  |  | Oracle ACS | MetaAge / LineBank | *Exadata到貨後執行
1-3 | EDW(IFRS)移轉階段 |  |  | 2026-09-14 | 2026-12-14 | [5 empty] | *10月底完成
1-3-1 | Exadata資料庫建立與GoldenGate安裝 | 2 | PROD | 2026-09-14 | 2026-09-15 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2 | EDW(IFRS)資料庫正式環境演練移轉 (1st Round) | 18 | PROD | 2026-10-05 | 2026-10-30 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2-1 | EDW(IFRS)資料庫升級OGG資料同步作業 | 15 | PROD | 2026-09-16 | 2026-10-08 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2-2 | CBK資料同步OGG資料同步作業 | 6 | PROD | 2026-10-01 | 2026-10-08 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2-3 | 19c ODS資料庫同步結果檢查 | 5 | PROD | 2026-10-12 | 2026-10-16 |  |  |  | Oracle ACS | MetaAge / LineBank | 比對資料庫物件數量、Table筆數以及資料內容抽樣
1-3-2-4 | 系統效能調校 | 3 | PROD | 2026-10-19 | 2026-10-21 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2-5 | AP驗證 | 6 | PROD | 2026-10-22 | 2026-10-30 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-2-6 | EDW(IFRS)升級移轉RunBook最終確認 | 5 | PROD | 2026-10-02 | 2026-10-06 |  |  |  | LineBank | Oracle ACS / MetaAge
1-3-2-7 | Exadata 加入 EMCC 監控 | 3 | PROD | 2026-10-22 | 2026-10-27 |  |  |  | MetaAge | LineBank
1-3-2-8 | EDW(IFRS)資料庫日常監控機制設定 | 2 | PROD | 2026-10-28 | 2026-10-29 |  |  |  | MetaAge | LineBank
1-3-2-9 | EDW(IFRS)資料庫備份機制設定 | 1 | PROD | 2026-10-30 | 2026-10-30 |  |  |  | MetaAge | LineBank
1-3-3 | 19c EDW(IFRS)資料庫/GolenGate 正式環境正式移轉 (2nd Round) | 31 | PROD | 2026-11-02 | 2026-12-14 |  |  |  | Oracle ACS | MetaAge / LineBank | *Oracle ACS 驗收工單
1-3-3-1 | 清空1st Round演練資料 | 1 | PROD | 2026-11-02 | 2026-11-02 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-3-2 | EDW(IFRS)資料庫升級OGG資料同步作業 | 14 | PROD | 115/11/3 | 115/11/20 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-3-3 | CBK資料同步OGG資料同步作業 | 5 | PROD | 115/11/16 | 115/11/20 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-3-4 | 上線前最終確認 | 5 | PROD | 115/11/23 | 115/11/27 |  |  |  | LineBank | Oracle ACS / MetaAge
1-3-3-5 | 系統切換 | 1 | PROD | 115/11/29 | 115/11/29 |  |  |  | Oracle ACS / LineBank | MetaAge / LineBank
1-3-3-6 | 清理移轉OGG環境 | 1 | PROD | 115/11/30 | 115/11/30 |  |  |  | Oracle ACS | MetaAge / LineBank
1-3-3-7 | 舊EDW(IFRS)資料庫x86環境升級(備案) | 1 | PROD - DR | 115/12/7 | 115/12/7 |  |  |  | MetaAge | LineBank
1-3-3-8 | EDW(IFRS)資料庫備援X86環境建置(備案) | 5 | PROD - DR | 115/12/8 | 2026-12-14 |  |  |  | MetaAge | LineBank
第二階段 - ELN 作業
2-1 | ELN移轉階段 |  |  | 2027-02-15 | 2027-03-12 | [5 empty] | *2027_Q1/Q2完成
2-1-1 | 龍潭機房環境與IP、防火牆網路資訊準備 | 5 | PROD | 2027-02-15 | 2027-02-19 |  |  |  | LineBank | MetaAge/LineBank
2-1-2 | ELN資料庫移轉演練 (1st Round) | 25 | PROD | 2027-02-22 | 2027-03-18 |  |  |  | LineBank | Oracle ACS / MetaAge
2-1-2-1 | 透過DataGuard建立Standby並切換(datapatch) | 5 | PROD | 2027-02-22 | 2027-03-01 |  |  |  | LineBank | Oracle ACS / MetaAge
2-1-2-2 | 系統效能調校 | 3 | PROD | 2027-03-02 | 2027-03-04 |  |  |  | Oracle ACS | MetaAge/LineBank
2-1-2-3 | AP驗證 | 7 | PROD | 2027-03-05 | 2027-03-15 |  |  |  | LineBank | Oracle ACS / MetaAge
2-1-2-4 | 上線前最終確認 | 4 | PROD | 2027-03-16 | 2027-03-19 |  |  |  | LineBank | Oracle ACS / MetaAge
2-1-2-5 | ELN移轉RunBook最終確認 | 5 | PROD | 2027-03-22 | 2027-03-26 |  |  |  | LineBank | MetaAge/LineBank
2-1-3 | ELN資料庫正式環境移轉至Exadata | 10 | PROD | 2027-03-29 | 116/4/11 |  |  |  | Oracle ACS | MetaAge/LineBank | *Oracle ACS 驗收工單 *停機要選02:30 batch job結束後
2-1-3-1 | 清空演練環境 | 1 | PROD | 2027-03-29 | 2027-03-29 |  |  |  | Oracle ACS | MetaAge/LineBank
2-1-3-2 | 透過DataGuard建立Standby | 6 | PROD | 2027-03-29 | 116/4/5 |  |  |  | Oracle ACS | MetaAge/LineBank
2-1-3-3 | ELN資料庫日常監控機制設定 | 1 | PROD | 116/4/6 | 116/4/6 |  |  |  | MetaAge | LineBank
2-1-3-4 | 系統切換 | 1 | PROD | 116/4/11 | 116/4/11 |  |  |  | Oracle ACS / LineBank | MetaAge
2-1-3-5 | ELN資料庫備份機制設定 | 1 | PROD | 116/4/11 | 116/4/11 |  |  |  | MetaAge | LineBank
2-2 | Oracle ODA X8-HA一座遷移至備援機房與升級 | 14 | PROD - DR | 2027-04-12 | 2027-04-29 |  |  |  | MetaAge | LineBank | *升級版本建議19.31
2-2-1 | ODA設備搬遷 | 3 | PROD - DR | 2027-04-12 | 2027-04-14 |  |  |  | MetaAge/寰成 | LineBank
2-2-2 | ODA設備檢測 | 1 | PROD - DR | 2027-04-15 | 2027-04-15 |  |  |  | MetaAge | LineBank
2-2-3 | Oracle ODA X8-HA安裝 | 3 | PROD - DR | 2027-04-16 | 2027-04-20 |  |  |  | MetaAge | LineBank
2-2-4 | ODA 加入 EMCC 監控 | 2 | PROD - DR | 2027-04-21 | 2027-04-22 |  |  |  | MetaAge | LineBank
2-2-5 | EDW(IFRS)資料庫備援ODA環境建置 | 6 | PROD - DR | 2027-04-21 | 2027-04-28 |  |  |  | Oracle ACS | MetaAge/LineBank
2-2-6 | EDW(IFRS)資料庫備援加入 EMCC 監控 | 1 | PROD | 2027-04-29 | 2027-04-29 |  |  |  | MetaAge | LineBank
3-1 | 舊環境下線 (備案)
3-1-1 | 準備下線程序 (關防火牆、監控DB移除、CYB移除、備份移除) | 5 | N/A | [5 empty] | LineBank
3-1-2 | EDW PRD/DR 關機 | 1 | N/A | [5 empty] | LineBank
3-1-3 | 通知IT 釋放Storage資源 | 1 | N/A | [5 empty] | LineBank
3-2 | 驗收完工交付階段 |  |  | 2027-05-03 | 2027-05-28
3-2-1 | Oracle Data Guard 教育訓練 | 3 | N/A | 2027-05-03 | 2027-05-05 |  |  |  | MetaAge | LineBank | *內容雙方議定
3-2-2 | 專案文件製作與交付 | 8 | N/A | 2027-05-05 | 2027-05-14 |  |  |  | MetaAge | LineBank | *LineBank(Ryan) 告知驗收文件之項目
3-2-3 | 專案初驗 | 5 | N/A | 2027-05-17 | 2027-05-21 |  |  |  | LineBank | MetaAge
3-2-4 | 專案複驗 | 5 | N/A | 2027-05-24 | 2027-05-28 |  |  |  | LineBank | MetaAge
On Schedule
Delay 1 Week
Delay 2 Weeks
Note on J4: 主責單位

## tracking issue
Item | Status | Issue | Create Date | Description | Impact | Close Date | Action
Ex. | Solved | VM Cluster creation | 2020-11-12 | SR 3-24619289181 VM Cluster creation took too long time | 1. ExaCC stop working from 2020/11/12 to 2020/11/28 2. we started the process eariler than FEIB's schedule, didn't impact to the project schedule 3. monthly consumption decreased 4K | 2020-11-28 | 1. FIEB CPS is using domain name for NTP server. This was acceptable setting when ExaCC deployed but Oracle does not accept domain name now. This cause the check for CPS DNS failed and OCI console did nothing. 2. 2020/11/27 Updated by Cloud Ops, customer DNS setting issue causes VM creation failed and kept to retry. 3. Cloud Ops apply workaround to bypass failure.

## 甘特圖
專案甘特圖
連線商銀EDW升級暨一體機建置專案
項目 | 任務名稱 | 天數 | 開始日期 | 結束日期 | 狀態 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01
0 | 前置作業 | 12 | 2026-05-01 | 2026-07-10
1 | 專案啟動 | 2 | 2026-05-28 | 2026-06-25
2 | 硬體建置 | 10 | 2026-07-15 | 2026-07-28
3 | UAT移轉 | 90 | 2026-07-02 | 2026-09-30
4 | CBK測試 | 4 | 2026-07-30 | 2026-08-04
5 | EDW移轉 | 145 | 2026-08-05 | 2026-10-23
6 | ELN移轉 | 23 | 2027-02-15 | 2027-03-12
7 | 教育訓練 | 3 | 2027-03-15 | 2027-03-17
8 | 完工結案階段 | 20 | 2027-03-18 | 2027-04-30